## Slide 1: Wisconsin Youth Treatment Initiative Lessons Learned and Formula for Success
Jason Cram, Wisconsin Department of Health Services
Janae Goodrich, UW-Madison Population Health Institute
Rachel Amos, UW-Madison Population Health Institute
Notes: Jason – introductions

## Slide 2: Background
Funded by a four-year grant from Substance Abuse and Mental Health Services Administration, October 2017 – September 2021.
Contracted with four clinics across the state to provide evidence-based treatment.
Selected evidence-based practice: Multidimensional Family Therapy (MDFT).
Notes: PHI

## Slide 3: Program Purpose
“The purpose of this program is to provide funding to improve treatment for adolescents and/or transitional aged youth with substance use disorders and/or co-occurring substance use and mental health disorders by assuring youth statewide access to evidence-based assessments, treatment models, and recovery services supported by the strengthening of the existing infrastructure system.”
https://www.samhsa.gov/grants/grant-announcements/ti-17-002
Notes: PHI

## Slide 4: Clinic Locations
Partner sites located in:
Rural and urban areas.
Areas with a low number of providers.
High areas of substance use/abuse.
Partner sites are:
County agency.
Hospital affiliation.
Non-profit private practice.
Notes: PHI

## Slide 5: Population Served
111 youth and young adults served
*Data as of July 2, 2021 – Source: SPARS Reports
Notes: PHI

## Slide 6: Preliminary Outcomes
Six-month follow-up outcomes
*Data as of July 2, 2021
(N = 68)
Source: SPARS Reports
Preliminary youth MDFT behavioral outcomes at discharge
96% lived at home/not in a placement
94% had no drug use other than Marijuana or alcohol
94% had no new arrests
81% used Marijuana/alcohol less than 10 days per month
74% in school or working
*Data as of September 30, 2020, (N = 89), Source: Years 1-3 Evaluation Report
Notes: PHI

## Slide 7: Successes
Structure for family therapy
Strengths of the MDFT model
Positive outcomes for youth and family
Alternative to inpatient treatment
Innovative opportunities for outreach
Notes: PHI

## Slide 8: Formula for Success
Notes: DHS

## Slide 9: Challenges to Implementation
Lack of planning grant
Lack of interested and qualified providers
Start-up challenges
Training delays
Staff retention
Notes: DHS

## Slide 10: Challenges to Implementation
Staff recruitment
Training and train-the-trainer models
Development of referral sources
Estimation of target age population
Evidence-based practice alignment with billing structure
Notes: DHS

## Slide 11: Challenges to Implementation
Wisconsin is largely rural with 5.8 million residents; 36% of the population living in 4 of 72 counties; and 44 of 72 counties having a population below 50,000.
Wisconsin does not have Medicaid expansion.
There is little financial incentive for a clinic or clinician to use an evidence-based practice.
Notes: DHS

## Slide 12: Implementation Drivers
Notes: DHS

## Slide 13: Lessons Learned
Lack of planning grant (leadership drivers)
  Utilize implementation science
  Apply the lessons learned – implementation teams
  Begin planning for future grants
  Engage potential vendors before application
Lack of interested and qualified providers (competency drivers)
  Address initiative overload early
  Engage potential vendors before application
  When possible, target specific vendors
  Begin sustainability planning immediately
Notes: DHS

## Slide 14: Lessons Learned
Start-up challenges (organization drivers)
  Consult with others in implementation of evidence-based practices
  Engage evidence-based practices trainers early and often
  Anticipate delays
Training delays (organization drivers)
  Engage evidence-based practices trainers early and often
  Establish a flexible training plan
  Plan for multiple training locations and times
  Consider virtual training when possible
Notes: DHS

## Slide 15: Lessons Learned
Staff retention (organization and competency and leadership drivers)
  Fully understand the training time and costs
  Appreciate that practicing an evidence-based practice to fidelity is not for everyone
  Focus on workforce development
  Increased reimbursement for evidence-based practice delivery
  Importance of a local champion
Staff recruitment (competency drivers)
  Workforce development
  Incentives
Notes: DHS

## Slide 16: Lessons Learned
Training and train-the-trainer models (leadership, competency, and organization drivers)
  Centralized trainer
  Collaborate with evidence-based practice developer
  Build in and budget for redundancy
Development of referral sources (organization driver)
  Immediate and continued outreach with local adaptation
  Advertising
  Forums for presenting model and Q&A
  Promote the benefits of evidence-based practices and the long-term cost savings
Notes: DHS

## Slide 17: Lessons Learned
Target age range and geography (organization and leadership drivers)
  Work to build consortiums
  Explore family and natural support engagement opportunities
  Use of video technology or telemedicine where applicable
Financial (organization and leadership drivers)
  Promote systems change at state and insurance levels
  Promote utilization of Medicaid reimbursement
Notes: DHS

## Slide 18: Data Collection Challenges and Lessons Learned
Challenges
  Amount of data collection required
  Alignment between data collection requirements
Lessons learned (organization and competency drivers)
  Training for staff
  Ongoing monitoring and reminders
  Dedicated staff time
  Local measurement of success
Notes: PHI

## Slide 19
Notes: DHS

## Slide 20: Formula for Implementation
Notes: DHS

## Slide 21: An Eye to the Future
Promote a sustainable system of care that meets the needs of a population through the utilization of evidence-based practices to fidelity.
Sustainability of existing sites
Workforce development
Implementation team
Develop in-house trainers
Decision support data system
Include potential vendors in the planning
Notes: PHI and DHS
  Sustainability of existing sites - PHI
  Workforce development - Jason
  Implementation team - Jason
  Develop in-house trainers - Jason
  Decision support data system - PHI
  Include potential vendors in the planning - DHS

## Slide 22: Contact Information
Jason Cram
Children, Youth, and Families Section Chief
Wisconsin Department of Health Services
jason.cram@dhs.wisconsin.gov
Janae Goodrich
Associate Researcher
University of Wisconsin-Madison Population Health Institute
jgoodrich@wisc.edu
Rachel Amos
Associate Research Specialist
University of Wisconsin-Madison Population Health Institute
reamos@wisc.edu